## f8 PG-WZP
| Name Of Company | Delhi Transco Limited
| Name of Project | Turnkey Project of Supply, Laying, Jointing, testing and commissioning of 220kV D/C 1x1000 sq.mm U/G XLPE cable from 220 kV S/Stn. Peeragarhi to Wazirpur Sub Stataion.
| Name of the transmission Element |  | 220 kv D/C Cable
Break up of Project Cost for Transmission System | [13 empty] | Form No: | F 8
No. | Break Down | As per original Estimate (In Crores) | Actual capital expenditure as on date 01.12.2014 | [9 empty] | Liabilities /Provisions | Variation (B-C-D) | Reason for variation
|  |  | 2010-11 (in INR) | 2011-12(in INR) |  | 2012-13(in INR) |  | 2013-14(in INR) |  | 2014-15(in INR) |  | Total In INR
A. | Transmission Line (U/G 220 KV XLPE 1X1000 sq. mm cable)
1 | Preliminary works
1.1 | Design & Engineering
1.2 | Preliminary investigation, Right of way , forest clearances, PTCC, general civil works etc. | - | 59757523 |  | 1855728 |  | 2902907 |  | -8630769 |  | 83651269 | 139536658 | 0
| Total Preliminary works |  | 59757523 |  | 1855728 |  | 2902907 |  | -8630769 |  | 83651269 | 139536658 | 0
2 | Cable Link material |  |  | USD | INR(@47.31 | USD | INR(@47.31 | USD | INR(@47.31 | USD | INR(@47.31 | INR
2.1 | 220KV Cross-linked Polyethylene insulated (XLPE) single core cable | 47.69 | 0 | 7877189.7884 | 372669848.89 | 819569.549 | 38773835.3628 | 0 | 0 | 0 | 0 | 411443684.2528 | 0
2.2 | 220KV XLPE cable straight through joint kit. | 5.82 | 0 | 1566000 | 74087460 | 0 | 0 | 0 | 0 | 0 | 0 | 74087460 | 0
2.3 | 220kV I/D & O/D XLPE cable end termination | 0.62 | 0 | 0 | 0 | 87000 | 4115970 | 0 | 0 | 0 | 0 | 4115970 | 4115970
2.4 | DTS System with multiplexer, Hardware and Software | 1.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | other auxiliary material | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9479078.91
2.6 | Spares | 0.36 | 0 | 72500 | 3429975 | 14500 | 685995 | 0 | 0 | 0 | 0 | 4115970 | 685995
2.7 | Erection, String & Civil work including foundation | 51.45 | 0 | 0 | 0 | 0 | 0 | 0 | 118001871.307 | 0 | 10484797.4424 | 128486668.7494 | 90000000
| Total Transmission line material | 107.77 | 0 | 9515689.7884 | 450187283.89 | 921069.549 | 43575800.3628 | 0 | 118001871.307 | 0 | 10484797.4424 | 622249753.0022 | 104281043.91
3 | Taxes and duties
3.1 | Custom duty | Inclusive in material cost | 0 | 0 | 91477541 | 0 | 13330501 | 0 | 0 | 0 | 1304270 | 106112312 | 0
3.2 | Other Taxes and duties (incl. Transportation) | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | Total Taxes and duties | 8.65 | 0 | 0 | 91477541 | 0 | 13330501 | 0 | 0 | 0 | 1304270 | 106112312 | 0
| Total -Transmission lines | 116.42 | 59757523 | 9515689.7884 | 543520552.89 | 921069.549 | 59809208.3628 | 0 | 109371102.307 | 0 | 95440336.4424 | 867898723.0022 | 104281043.91
Other charges
i | Type testing & training charges | 1.02 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
ii | Contingency and Other Charges | 5.64
iii | Engineering & Administrative Charges | 9.25
| Total other charges | 15.91
12 | IDC, FC, FERV & Hedging Cost | 8.8
13 | Capital Cost incl IDC, FC, FERV & Hedging Cost | 141.13
[12 empty] | Oct-Dec 14 | Jan - Mar 15
[7 empty] | 2902907 |  | -8630769 |  | 7378446 | 76272823 | 9393950
[7 empty] | 13330501 |  | 0 |  | 1304270 | 17882317 | 4658400
[6 empty] | 3rd RB | 10996831.02 |  | 45446140 |  | 3654000 | 94155140 | 14052350
[6 empty] | 2nd RB | 44197174.2084 |  | 8964610 |  | 12336716
[6 empty] | 3rd LC | 31832927.1192 |  | 18648445
[7 empty] | 103260340.3476 |  | 871824.86
65300250.86
1854

## f9 PG-WZP
| Name Of Company | Delhi Transco Limited
| Name of Project | Turnkey Project of Supply, Laying, Jointing, testing and commissioning of 220kV D/C 1x1000 sq.mm U/G XLPE cable from 220 kV S/Stn. Peeragarhi to Wazirpur Sub Stataion. .
| Name of the transmission Element |  | 220 kV D/C cable
Break-up of Construction/ Supply/ Service packages | [6 empty] | Form No: | F9
| Particulars | 1 | 2 | 3 | 4 | 5 | 6 | ----
1 | Name/ No. of Construction / Supply / Service Package | 1: Peeragarhi to Wazirpur Industrial Area
2 | Scope of works1 (in line with head of cost break-ups as applicable) | 1: Supply, Laying, Jointing, Testing and Commissioning of 220KV XLPE cable of 1000 sq.mm. D/C, U/G transmission line
3 | Whether awarded through ICB/DCB/ Depatmentally/ Deposit Work | 1: ICB
4 | No. of bids received | 1: 8
5 | Date of Award | 1: 28.05.2010
6 | Date of Start of work | 1: 28.05.2010
7 | Date of Completion of Work | 1: Work in progress.Expected to be completed by 31.05.2014
8 | Value of Award in (Rs. ) | 1: USD 15846156.00+INR 370481926.60= Rs.1116994335.76 @ usd 47.11 conversion rate
9 | Firm or With Escalation in prices | 1: Escalation of prices with decrease in awarded cost of Rs. 1.06 Crores
10 | Actual capitalexpenditure till the completion or up to COD whichever is earlier(Rs.Cr.) | 1: ----
11 | Taxes & Duties and IEDC | 1: Shall be provided by Finance
12 | IDC, FC, FERV & Hedging Cost | 1: Shall be provided by Finance
13 | Sub -total (9+10+11) | 1: ----
1 The scope of work in any package should be indicated in conformity of Capital cost break-up for the coal/lignite based plants in the Form 8 to the extent possible. In case of Gas/Liquid fuel based projects, break down in the similar manner in the relevent heads as per Form 10.
2 If there is any package, which need to be shown in Indian Rupee and foreign currency(ies), the same should be shown separatly alongwith the currency, the exchange rate and the date e.g. Rs. 80 Cr + US$50 mn = Rs.320 Cr at US$ = Rs 48 as on say 1 April 2011
Petitioner

## F14 Mundka (hidden)
Name of Company: |  |  | Delhi Transco Limited
Name of the Project: |  |  | Turnkey Project of Supply, Laying, Jointing, testing and commissioning of 220kV D/C 1x1000 sq.mm U/G XLPE cable from 400/220 kV S/Stn. Mundka to Peeragarhi Sub Stataion. .
Name of the Transmission Element: |  |  | 220 KV D/C Cable
Statement of Additional Capitalisation after COD |  |  |  |  | Form No: | F14
Rs Crores
No | Year | Work/ Equipment proposed to be added after COD up to Cut off Date/ Beyond Cut off Date | Amount capitalised and Proposed to be capitalised | Justification | Regulations under which covered | Admitted Cost1
1
2
3
4
5
Note:
1 Fill the form in chronological order year wise along with detailed justification clearly bring out the necessity and the benefits accruing to the benficiaries.
2 In case initial spares are purchased alongwith any equipment, then the cost of such spares should be indicated separately. e.g. Rotor - 50 Crs. Initial spares- 5 Crs.
Petitioner

## f4 PG-WZP
Name of Company: |  | Delhi Transco Limited
Name of the Project: |  | Turnkey Project of Design, Supply, Laying, Jointing, Testing and Commissioning of 220KV XLPE cable of 1000 sq.mm. D/C, U/G transmission line between 220KV GIS substation Peeragarhi and 220kV GIS substation Wazirpur Industrial Area
Name of the Transmission Element: |  | 220 kv D/C Cable
Abstract of admitted Capital Cost for the existing Project |  |  |  | Form No: | F4
| Particulars | Unit | Details
1 | Capital Cost as admitted by DERC | Rs Crores | 141.13 on dated 01.02.2010
2 | Capital cost admitted as on 1.12.2014
3 | Foreign Component, if any (In Million US $ or the relevant Currency) | USD | 10.44
4 | Domestic Component | Rs Crores | 37.41
5 | Foreign Exchange rate considered for the admitted Capital cost |  | 47.31
6 | Hedging cost, if any, considered for the admitted Capital cost | Rs Crores | Not Considered
7 | Total Capital cost admitted (4+5+6) | Rs Crores | Rs. 86.79 Cr as on 1.12.2014
Petitioner

## f7 PG-WZP
f7
Name of Company: |  | Delhi Transco Limited
Name of the Project: |  | Turnkey Project of Design, Supply, Laying, Jointing, Testing and Commissioning of 220KV XLPE cable of 1000 sq.mm. D/C, U/G transmission line between 220KV GIS substation Peeragarhi and 220kV GIS substation Wazirpur Industrial Area
Name of the Transmission Element: |  | 220 KV D/C Cable
Capital Cost Estimates and Schedule of Commissioning for New projects |  | Form No: | F7
| Board of Director/ Agency approving the Capital cost estimates: | DELHI TRANSCO LIMITED
| Date of approval of the Capital cost estimates: | 16th JUNE 2009
|  | Present Day Cost | Completed Cost
| Price level of approved estimates | As on 1.12.2014 | As on Scheduled COD of the Station
| Foreign Exchange rate considered for the Capital cost estimates | 1 USD = 47.31 INR | ---- | 10436759.36
Capital Cost excluding IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | USD 10.44 Million | ---- | 128487002.6524
| Domestic Component (Rs. Lakhs) | Rs. 3741.36 Lakhs | ---- | 139536658
| Capital cost excluding IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | Rs. 8678.99 Lakhs | ---- | 106112312
374135972.6524
IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | Shall be provided by Finanace Deptt. |  | 622250087.974
Domestic Component (Rs. Lakhs)
Total IDC, FC, FERC & Hedging Cost (Rs. Lakhs)
| Rate of taxes & duties considered | Shall be provided by Finanace Deptt.
Capital cost Including IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | Shall be provided by Finanace Deptt.
Domestic Component (Rs. Lakhs)
Capital cost Including IDC, FC, FERC & Hedging Cost (Rs. Lakhs)
Schedule of Commissioning
| COD of Unit-I/ Block-I | The transmission link project is expected to be commissioned in Financial Year 2015-16.
COD of Unit-II/ Block-II
-------------------------
---------------------------
COD of last Unit/ Block
Note:
1. Copy of approval letter should be enclosed.
2. Details of Capital cost are to be furnished as per Form 8 or Form 9 as applicable.
3. Details of IDC & Financing Charges are to be furnished as per Form 10
Petitioner