## f.4
Name of Company: |  | Delhi Transco Limited
Name of the Project: |  | Turnkey Project of Supply, Laying, Jointing, testing and commissioning of 220kV D/C 1x1000 sq.mm U/G XLPE cable from 220 kV S/Stn. Shalimar Bagh to Wazirpur Sub Stataion.
Name of the Transmission Element: |  | 220 kV D/C XLPE Cable Project
Abstract of admitted Capital Cost for the existing Project |  |  |  | Form No: | F4
| Particulars | Unit | Details
1 | Capital Cost as admitted by DERC | Crores | 64.79
2 | Capital cost admitted as on
3 | Foreign Component, if any (In Million US $ or the relevant Currency) | USD | USD 5775646
4 | Domestic Component | Crores | INR 89350363.0+Custom duty INR 49217413.23
5 | Foreign Exchange rate considered for the admitted Capital cost |  | @ USD 47.19 conversion rate
6 | Hedging cost, if any, considered for the admitted Capital cost
7 | Total Capital cost admitted | Crores | Equivalent INR 41.11
As per LOA awarded to M/s. TBEA the equivalent INR 41.11 Crore including Coustom Duty
Petitioner

## f.7
Name of Company: |  | Delhi Transco Limited
Name of the Project: |  | Turnkey Project of Supply, Laying, Jointing, testing and commissioning of 220kV D/C 1x1000 sq.mm U/G XLPE cable from 220 kV S/Stn. Shalimar Bagh to Wazirpur Sub Stataion.
Name of the Transmission Element: |  | 220 kV D/C XLPE Cable Project
Capital Cost Estimates and Schedule of Commissioning for New projects |  | Form No: | F7
| Board of Director/ Agency approving the Capital cost estimates: | DTL Board
| Date of approval of the Capital cost estimates: | 20.06.2008
|  | Present Day Cost | Completed Cost
| Price level of approved estimates | As of End of 2nd Qtr. Of the year 2014-2015 | As on Scheduled COD of the Station
| Foreign Exchange rate considered for the Capital cost estimates | 47.19 (as BID Opening)
Capital Cost excluding IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | USD 4149795.55
| Domestic Component (Rs. Lakhs) | Rs. 53995826.95
| Capital cost excluding IDC, FC, FERC & Hedging Cost (Rs. Lakhs) |  | Work is in progress
IDC, FC, FERC & Hedging Cost
Foreign Component, if any (In Million US $ or the relevant Currency)
Domestic Component (Rs. Lakhs)
| Total IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | Shall be provided by Finance deptt.
Rate of taxes & duties considered
Capital cost Including IDC, FC, FERC & Hedging Cost
Foreign Component, if any (In Million US $ or the relevant Currency)
Domestic Component (Rs. Lakhs)
Capital cost Including IDC, FC, FERC & Hedging Cost (Rs. Lakhs)
Schedule of Commissioning
| 220 KV Circuit-I | Commisioned on 20/06/2014
| 220 KV Circuit-II | Commisioned on 19/06/2014
COD of last Unit/ Block
Note:
1. Copy of approval letter should be enclosed.
2. Details of Capital cost are to be furnished as per Form 8 or Form 9 as applicable.
3. Details of IDC & Financing Charges are to be furnished as per Form 10
| 4. Both 220 KV Circuits ARE IN Commercial Operation since 24/06/2014 |  | Petitioner

## F8 SMB-WAZ2014
| Name Of Company | Delhi Transco Limited
| Name of Project | Turnkey Project of Supply, Laying, Jointing, testing and commissioning of 220kV D/C 1x1000 sq.mm U/G XLPE cable from 220 kV S/Stn. Shalimar Bagh to Wazirpur Sub Stataion.
| Name of the transmission Element | 220 kV D/C XLPE Cable Project
Break up of Project Cost for Transmission System Form No F-8
No. | Break Down | As per original Estimate (In Crores) | Actual capital expenditure as on date 30/11/2014 | Liabilities /Provisions | Variation (B-C-D) | Reason for variation
| A | B | C | D | E | F
Total In INR
A. | Transmission Line | N/A
B. | Substations | N/A
C. | U/G 220 KV Cable Link
1 | Preliminary works
1.1 | Design & Engineering
1.2 | Preliminary investigation, Right of way , forest clearances, PTCC, general civil works etc. | 0.35 | 2972896 | 0
| Total Preliminary works | 0.35 | 2014 | 0
2 | Cable Link material
2.1 | 220KV Cross-linked Polyethylene insulated (XLPE) single core cable | 25.418 | 140313851.949 | 67361129.9952
2.2 | 220KV XLPE cable straight through joint kit. | 3.307 | 25195200
2.3 | 220kV I/D & O/D XLPE cable end termination | 0.88 | 6298800
2.4 | DTS System with multiplexer, Hardware and Software | 5 | 3707659.8
2.5 | Spares | 0.42 | 4363231.25
2.6 | Expatriate personnel |  | 11226610.1387
2.7 | Domestic Material | 1.014 | 10717889.76 | 15519320.28
2.7 | F&I,Erection, Civil work including foundation | 13.447 | 44990666.62
| Total Transmission line material | 49.486 | 246813909.5177 | 82880450.2752
3 | Taxes and duties
3.1 | Custom duty |  | 48512831.8 | 0
3.2 | Other Taxes and duties (incl. Transportation) | 3.824
3.3 | Total Taxes and duties | 3.824 | 48512831.8
| Total -Transmission lines | 53.66 | 295328755.3177
Other charges
i | Type testing & training charges | 1.25 | 0
ii | Contingency and Other Charges | 2.598 | 0
iii | Engineering & Administrative Charges | 4.206
| Total other charges | 8.054
12 | IDC, FC, FERV & Hedging Cost | 3.067 |  | 0
13 | Capital Cost incl IDC, FC, FERV & Hedging Cost | 64.781 |  | 0
Note.
1. In case of time and cost over run,a detailed note giving reasons of such time and cost over run should be submitted clearly bring out the agency responsible and whether such time and cost over run was beyond the control of the generating company
2. The exchange rate considered at the time of payment is 1 USD=INR 45.25
3. The exchange rate considered for balance payment/liabilities is 1 USD=INR 60.26

## F9SMB-
Name Of Company |  | Delhi Transco Limited
Name of Project |  | Turnkey Project of Supply, Laying, Jointing, testing and commissioning of 220kV D/C 1x1000 sq.mm U/G XLPE cable from 220 kV S/Stn. Shalimar Bagh to Wazirpur Sub Stataion.
Name of the transmission Element |  | 220 kV D/C cable | [5 empty] | in INR
Break-up of Construction/ Supply/ Service packages | [6 empty] | Form No: | F9
| Particulars | 1 | 2 | 3 | 4 | 5 | 6 | ----
1 | Name/ No. of Construction / Supply / Service Package | 1: Shalimar Bagh to Wazirpur
2 | Scope of works1 (in line with head of cost break-ups as applicable) | 1: Supply, Laying, Jointing, Testing and Commissioning of 220KV XLPE cable of 1000 sq.mm. D/C, U/G transmission line
3 | Whether awarded through ICB/DCB/ Depatmentally/ Deposit Work | 1: ICB
4 | No. of bids received | 1: 7
5 | Date of Award | 1: 28.05.2010
6 | Date of Start of work | 1: 28.05.2010
7 | Date of Completion of Work | 1: 20/06/2014
8 | Value of Award2 in (Rs. Lakhs) | 1: USD5775646+INR89350363.0+custom duty INR 49217413.23 = Rs.41.11 Crore @ USD 47.19 conversion rate
9 | Firm or With Escalation in prices | 1: Price variation on cable supply only.
10 | Actual capital expenditure till the completion or up to COD whichever is earlier(Rs.Cr.)
11 | Taxes & Duties and IEDC
12 | IDC, FC, FERV & Hedging Cost
13 | Sub -total (9+10+11)
1 The scope of work in any package should be indicated in conformity of Capital cost break-up for the coal/lignite based plants in the Form 8 to the extent possible. In case of Gas/Liquid fuel based projects, break down in the similar manner in the relev
2 If there is any package, which need to be shown in Indian Rupee and foreign currency(ies), the same should be shown separatly alongwith the currency, the exchange rate and the date e.g. Rs. 80 Cr + US$50 mn = Rs.320 Cr at US$ = Rs 48 as on say 1 April
Petitioner