## F4
Name of Company: |  | Delhi Transco Ltd
Name of the Project: |  | Erection, testing & commissioning of 220 KV Double circuit over head Transmission Tower Line from Maharani Bagh 400 KV S/Stn to Gazipur 220 KV S/Stn. [T – 121]
Name of the Transmission Element: |  | 220KV Overhead Transmission Line
Abstract of admitted Capital Cost for the existing Project |  |  |  | Form No: | F4
| Particulars | Unit | Details
1 | Capital Cost as admitted by DERC | Rs. Lakh | 1878.20
2 | Capital cost admitted as on |  | 04.12.2007
3 | Foreign Component, if any (In Million US $ or the relevant Currency) |  | NA
4 | Domestic Component | Rs. Lakh | 1878.20
5 | Foreign Exchange rate considered for the admitted Capital cost |  | NA
6 | Hedging cost, if any, considered for the admitted Capital cost | Rs. Lakh | 195.80
7 | Total Capital cost admitted | Rs. Lakh | 2074
Petitioner

## F7
Name of Company: |  | Delhi Transco Ltd
Name of the Project: |  | Erection, testing & commissioning of 220 KV Double circuit over head Transmission Tower Line from Maharani Bagh 400 KV S/Stn to Gazipur 220 KV S/Stn.
Name of the Transmission Element: |  | 220KV Overhead Transmission Line
Capital Cost Estimates and Schedule of Commissioning for New projects |  | Form No: | F7
Board of Director/ Agency approving the Capital cost estimates:
| Date of approval of the Capital cost estimates: | 13.12.2006
|  | Present Day Cost | Completed Cost
| Price level of approved estimates | As of End of 2nd Qtr. Of the year 2014 | As on Scheduled COD of the Station
| Foreign Exchange rate considered for the Capital cost estimates | NA | NA
Capital Cost excluding IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA | NA
| Domestic Component (Rs. Lakhs) | 160333090 | 160333090
| Capital cost excluding IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | 160333090 | 160333090
IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA | NA
| Domestic Component (Rs. Lakhs) | 160333090 | 160333090
| Total IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | finance entry | finance entry
| Rate of taxes & duties considered | i/c taxes | i/c taxes
Capital cost Including IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA | NA
| Domestic Component (Rs. Lakhs) | 160333090 | 160333090
| Capital cost Including IDC, FC, FERC & Hedging Cost (Rs. Lakhs) |  | Both Ckt have been commissioned, however some patty work and reconciliation of DTL supplied material is in progress.
Schedule of Commissioning
| COD of Unit-I/ Block-I |  | 25./06/2014
| COD of Unit-II/ Block-II |  | 11/09/2014 (test charge 9/7/2014)
-------------------------
---------------------------
| COD of last Unit/ Block | 540Days
Note:
1. Copy of approval letter should be enclosed.
2. Details of Capital cost are to be furnished as per Form 8 or Form 9 as applicable.
3. Details of IDC & Financing Charges are to be furnished as per Form 10
Petitioner

## F8
Name of Company: |  |  |  | Delhi Transco Ltd
Name of the Project: |  |  |  | Erection, testing & commissioning of 220 KV Double circuit over head Transmission Tower Line from Maharani Bagh 400 KV S/Stn to Gazipur 220 KV S/Stn.
Name of the Transmission Element: |  |  |  | 220KV Overhead Transmission Line
Break-up of Project Cost for Transmission System |  |  |  |  | Form No: | F8
Rs Crores
No | Break Down | As per original estimates | Actual capital expenditure as on COD | Liabilities/ provisions | Variation (B-C-D) | Reasons for Variation
| A | B | C | D | E | F
A | Transmission Line | l
1 | Preliminary works | [5 empty] | OPG
1.1 | Design & Engineering |  | 0 |  |  |  | Qty | Rate | Amount
1.2 | Priliminary investigation,Right of way, forest clearance, PTCC , general civil works etc. |  | 22700000 |  |  |  | 8.369 | 177919 | 1489004.111
| Total Preliminary works | 0 | 22700000 |  |  |  | 6 | 4484 | 26904
2 | Transmission Lines material | [5 empty] | 62 | 4343 | 269266
2.1 | Towers Steel | 27558000 | 32640000 | Appox. 12500000 Work out cost after reconciliation |  |  | 80 | 1174 | 93920
2.2 | Conductor | 9540000 | 10350000 |  |  |  | 2 | 16295 | 32590
2.3 | Earth Wire/OPGW | 4173500 | 2274832 |  |  |  | 40 | 659 | 26360
2.4 | Insulators | 3416601.6 | 8595350 |  |  |  | 2 | 4343 | 8686
2.5 | Hardware Fittings | 1428600 | 1427599 |  |  |  |  | A | 1946730.111
2.6 | Conductor & Earthwire accessories | 279200 | 176473 |  |  |  | B (Service @ 15 on A) |  | 292009.5167
2.7 | Spares |  | 0 |  |  |  | ST @ 12.5% on B |  | 36092.3763
2.8 | Erection, Stringing & Civil works including foundation | 17900000 | 82168836 |  |  |  | Total |  | 2274832.0039
| Total Transmission Line Materials | 64295901.6 | 137633090
3 | Taxes and Duties |  | 0
3.1 | Custom Duty | 0 | 0
3.2 | Other Taxes & Duties | 10573117.38 | 0
| Total Taxes & Duties | 10573117.38 | 0
| Total -Transmission lines | 74869018.98 | 137633090
B. | Substations
4 | Preliminary works & land
4.1 | Design & Engineering
4.2 | Land
4.3 | Site preparation
| Total Preliminary works & land | 0
5 | Civil Works
5.1 | Control Room & Office Building including HVAC
5.2 | Township & Colony
5.3 | Roads and Drainage
5.4 | Foundation for structures
5.5 | Misc. civil works
| Total Civil Works | 0
6 | Substation Equipments
6.1 | Switchgear (CT,PT, Circuit Breaker, Isolator etc)
6.2 | Transformers
6.3 | Compensating Equipment( Reactor, SVCs etc)
6.4 | Control , Relay & Protection Panel
6.5 | PLCC | [6 empty] | 2009-10 | 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15
6.6 | HVDC package
6.7 | Bus Bars/ conductors/Insulators
6.8 | Outdoor lighting
6.9 | Emergency D.G. Set
6.1 | Grounding System
6.11 | Structure for switchyard
| Total Substation Equipments | 0
7 | Spares
8 | Taxes and Duties
8.1 | Custom Duty
8.2 | Other Taxes & Duties
| Total Taxes & Duties | 0
| Total (Sub-station) | 0
9 | Construction and pre-commissioning expenses
9.1 | Site supervision & site admn.etc.
9.2 | Tools and Plants
9.3 | construction Insurance
| Total Construction and pre commissioning expenses | 0
10 | Overheads
10.1 | Establishment
10.2 | Audit & Accounts
10.3 | Contingency
| Total Overheads | 0
11 | Total Cost (Plant and Equipment) | 74869018.98 | 160333090
12 | IDC, FC, FERV & Hedging Cost |  | finance entry
12.1 | Interest During Construction (IDC) | 19580549.13
12.2 | Financing Charges (FC)
12.3 | Foreign Exchange Rate Variation (FERV)
12.4 | Hedging Cost
| Total of IDC, FC, FERV & Hedging Cost | 19580549.13
13 | Capital Cost incl IDC, FC, FERV & Hedging Cost | 94449568.11 | Both Ckt have been commissioned, however some patty work and reconciliation of DTL supplied material is in progress.
Note:
1. In case of time & Cost over run, a detailed note giving reasons of such time and cost over run should be submitted clearly bring out the agency responsible and whether such time & cost over run was beyond the control of the generating company.
Petitioner

## F9
Name of Company: |  | Delhi Transco Ltd
Name of the Project: |  | Erection, testing & commissioning of 220 KV Double circuit over head Transmission Tower Line from Maharani Bagh 400 KV S/Stn to Gazipur 220 KV S/Stn. [T – 121]
Name of the Transmission Element: |  | 220KV Overhead Transmission Line
Break-up of Construction/ Supply/ Service packages | [6 empty] | Form No: | F9
| Particulars | 1 | 2 | 3 | 4 | 5 | 6 | ----
1 | Name/ No. of Construction / Supply / Service Package
2 | Scope of works1 (in line with head of cost break-ups as applicable)
3 | Whether awarded through ICB/DCB/ Depatmentally/ Deposit Work | DCB
4 | No. of bids received | 2
5 | Date of Award | 23.03.2009
6 | Date of Start of work | 23.03.2009
7 | Date of Completion of Work | Both Ckt have been commissioned on 25/06/2014 & 11/09/2014 (test charge on 09/07/2014), however some patty work and reconciliation of DTL supplied material is in progress.
8 | Value of Award2 in (Rs. Lakhs) | 934 (ETC portion only)
9 | Firm or With Escalation in prices | with escalation
10 | Actual capitalexpenditure till the completion or up to COD whichever is earlier(Rs.Cr.)
11 | Taxes & Duties and IEDC | Above cost is inclusive
12 | IDC, FC, FERV & Hedging Cost | To be furnished by Finance
13 | Sub -total (9+10+11)
1 The scope of work in any package should be indicated in conformity of Capital cost break-up for the coal/lignite based plants in the Form 8 to the extent possible. In case of Gas/Liquid fuel based projects, break down in the similar manner in the relevent heads as per Form 10.
2 If there is any package, which need to be shown in Indian Rupee and foreign currency(ies), the same should be shown separatly alongwith the currency, the exchange rate and the date e.g. Rs. 80 Cr + US$50 mn = Rs.320 Cr at US$ = Rs 48 as on say 1 April 2011
Petitioner

## T-140 4
Name of Company: |  | Delhi Transco Ltd
Name of the Project: |  | Erection, testing, commissioning of 220 KV Double circuit over head tower line by Loop In - Loop out of Kanjhawala - Najafgarh Transmission line at 400/220 KV S/Stn. Mundka.
Name of the Transmission Element: |  | 220KV Overhead Transmission Line
Abstract of admitted Capital Cost for the existing Project |  |  |  | Form No: | F4
| Particulars | Unit | Details
1 | Capital Cost as admitted by DERC | Rs. Lakh | 961.00
2 | Capital cost admitted as on |  | 03.07.2009
3 | Foreign Component, if any (In Million US $ or the relevant Currency) |  | NA
4 | Domestic Component | Rs. Lakh | 961 |  |  | 1025
5 | Foreign Exchange rate considered for the admitted Capital cost |  | NA |  |  | 64
6 | Hedging cost, if any, considered for the admitted Capital cost | Rs. Lakh | 64 |  |  | 961
7 | Total Capital cost admitted | Rs. Lakh | 1025
Petitioner

## T-140 7
Name of Company: |  | Delhi Transco Ltd
Name of the Project: |  | EErection, testing, commissioning of 220 KV Double circuit over head tower line by Loop In - Loop out of Kanjhawala - Najafgarh Transmission line at 400/220 KV S/Stn. Mundka.
Name of the Transmission Element: |  | 220KV Overhead Transmission Line
Capital Cost Estimates and Schedule of Commissioning for New projects |  | Form No: | F7
Board of Director/ Agency approving the Capital cost estimates:
| Date of approval of the Capital cost estimates: | 10.02.2009
|  | Present Day Cost | Completed Cost
| Price level of approved estimates | As of End of 2nd Qtr. Of the year 2014 | As on Scheduled COD of the Station
| Foreign Exchange rate considered for the Capital cost estimates | NA
Capital Cost excluding IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA
| Domestic Component (Rs. Lakhs) | 315.65
| Capital cost excluding IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | 315.65
IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA
| Domestic Component (Rs. Lakhs) | finance entry
| Total IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | finance entry
| Rate of taxes & duties considered | i/c
Capital cost Including IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA
| Domestic Component (Rs. Lakhs) | 315.65
| Capital cost Including IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | finance entry | Work in progress
Schedule of Commissioning
COD of Unit-I/ Block-I
COD of Unit-II/ Block-II
-------------------------
---------------------------
| COD of last Unit/ Block | 12 months
Note:
1. Copy of approval letter should be enclosed.
2. Details of Capital cost are to be furnished as per Form 8 or Form 9 as applicable.
3. Details of IDC & Financing Charges are to be furnished as per Form 10
Petitioner

## T-140 8
Name of Company: |  | #REF! |  | Delhi Transco Ltd
Name of the Project: |  | #REF! |  | EErection, testing, commissioning of 220 KV Double circuit over head tower line by Loop In - Loop out of Kanjhawala - Najafgarh Transmission line at 400/220 KV S/Stn. Mundka.
Name of the Transmission Element: |  | #REF! |  | 220KV Overhead Transmission Line
Break-up of Project Cost for Transmission System |  |  |  |  | Form No: | F8
Rs Crores
No | Break Down | As per original estimates | Actual capital expenditure as on COD | Liabilities/ provisions | Variation (B-C-D) | Reasons for Variation
| A | B | C | D | E | F
A | Transmission Line | l
1 | Preliminary works
1.1 | Design & Engineering
1.2 | Priliminary investigation,Right of way, forest clearance, PTCC , general civil works etc. |  | 65000
| Total Preliminary works | 0
2 | Transmission Lines material
2.1 | Towers Steel | 30639664 | 14700000
2.2 | Conductor | 16523796
2.3 | Earth Wire/OPGW | 2130825
2.4 | Insulators | 5402308
2.5 | Hardware Fittings | 1520136
2.6 | Conductor & Earthwire accessories | 2527455
2.7 | Spares | 100000
2.8 | Erection, Stringing & Civil works including foundation | 19101500 | 16800000
| Total Transmission Line Materials | 77945684 | 31500000
3 | Taxes and Duties
3.1 | Custom Duty | 0 | 0
3.2 | Other Taxes & Duties | 10573117.38 | 0
| Total Taxes & Duties | 10573117.38 | 0
| Total -Transmission lines | 88518801.38 | 31565000
B. | Substations
4 | Preliminary works & land
4.1 | Design & Engineering
4.2 | Land
4.3 | Site preparation
| Total Preliminary works & land | 0
5 | Civil Works
5.1 | Control Room & Office Building including HVAC
5.2 | Township & Colony
5.3 | Roads and Drainage
5.4 | Foundation for structures
5.5 | Misc. civil works
| Total Civil Works | 0
6 | Substation Equipments
6.1 | Switchgear (CT,PT, Circuit Breaker, Isolator etc)
6.2 | Transformers
6.3 | Compensating Equipment( Reactor, SVCs etc)
6.4 | Control , Relay & Protection Panel
6.5 | PLCC
6.6 | HVDC package
6.7 | Bus Bars/ conductors/Insulators
6.8 | Outdoor lighting
6.9 | Emergency D.G. Set
6.1 | Grounding System
6.11 | Structure for switchyard
| Total Substation Equipments | 0
7 | Spares
8 | Taxes and Duties
8.1 | Custom Duty
8.2 | Other Taxes & Duties
| Total Taxes & Duties | 0
| Total (Sub-station) | 0
9 | Construction and pre-commissioning expenses
9.1 | Site supervision & site admn.etc.
9.2 | Tools and Plants
9.3 | construction Insurance
| Total Construction and pre commissioning expenses | 0
10 | Overheads
10.1 | Establishment
10.2 | Audit & Accounts
10.3 | Contingency
| Total Overheads | 0
11 | Total Cost (Plant and Equipment) | 88518801.38 | 31565000
12 | IDC, FC, FERV & Hedging Cost
12.1 | Interest During Construction (IDC) | 6400902
12.2 | Financing Charges (FC)
12.3 | Foreign Exchange Rate Variation (FERV)
12.4 | Hedging Cost
| Total of IDC, FC, FERV & Hedging Cost | 6400902
13 | Capital Cost incl IDC, FC, FERV & Hedging Cost | 94919703.38 | Work in Progess
Note:
1. In case of time & Cost over run, a detailed note giving reasons of such time and cost over run should be submitted clearly bring out the agency responsible and whether such time & cost over run was beyond the control of the generating company.
Petitioner

## T-140 9
Name of Company: |  | Delhi Transco Ltd
Name of the Project: |  | EErection, testing, commissioning of 220 KV Double circuit over head tower line by Loop In - Loop out of Kanjhawala - Najafgarh Transmission line at 400/220 KV S/Stn. Mundka.
Name of the Transmission Element: |  | 220KV Overhead Transmission Line
Break-up of Construction/ Supply/ Service packages | [6 empty] | Form No: | F9
| Particulars | 1 | 2 | 3 | 4 | 5 | 6 | ----
1 | Name/ No. of Construction / Supply / Service Package
2 | Scope of works1 (in line with head of cost break-ups as applicable)
3 | Whether awarded through ICB/DCB/ Depatmentally/ Deposit Work | DCB
4 | No. of bids received | 3
5 | Date of Award | 28.08.2009
6 | Date of Start of work | 28.08.2009
7 | Date of Completion of Work | Work in progress
8 | Value of Award2 in (Rs. Lakhs) | 302 (ETC portion only)
9 | Firm or With Escalation in prices | with escalation
10 | Actual capitalexpenditure till the completion or up to COD whichever is earlier(Rs.Cr.)
11 | Taxes & Duties and IEDC | Above cost is inclusive
12 | IDC, FC, FERV & Hedging Cost | To be furnished by Finance
13 | Sub -total (9+10+11)
1 The scope of work in any package should be indicated in conformity of Capital cost break-up for the coal/lignite based plants in the Form 8 to the extent possible. In case of Gas/Liquid fuel based projects, break down in the similar manner in the relevent heads as per Form 10.
2 If there is any package, which need to be shown in Indian Rupee and foreign currency(ies), the same should be shown separatly alongwith the currency, the exchange rate and the date e.g. Rs. 80 Cr + US$50 mn = Rs.320 Cr at US$ = Rs 48 as on say 1 April 2011
Petitioner

## T-146
Name of Company: |  | Delhi Transco Ltd
Name of the Project: |  | Erection, testing, commissioning of 220 KV Double circuit over head tower line to provide infeed to proposed 220KV /66KV Rohini-II S/Strn from existing 400 /220KV S/Stn. Bawana
Name of the Transmission Element: |  | 220KV Overhead Transmission Line
Abstract of admitted Capital Cost for the existing Project |  |  |  | Form No: | F4
| Particulars | Unit | Details
1 | Capital Cost as admitted by DERC | Rs. Lakh | 1648
2 | Capital cost admitted as on |  | 04.12.2007
3 | Foreign Component, if any (In Million US $ or the relevant Currency) |  | NA
4 | Domestic Component | Rs. Lakh | 1648
5 | Foreign Exchange rate considered for the admitted Capital cost |  | NA
6 | Hedging cost, if any, considered for the admitted Capital cost | Rs. Lakh | 94.9
7 | Total Capital cost admitted | Rs. Lakh | 1743
Petitioner

## T-146 7
Name of Company: |  | Delhi Transco Ltd
Name of the Project: |  | Erection, testing, commissioning of 220 KV Double circuit over head tower line to provide infeed to proposed 220KV /66KV Rohini-II S/Strn from existing 400 /220KV S/Stn. Bawana
Name of the Transmission Element: |  | 220KV Overhead Transmission Line
Capital Cost Estimates and Schedule of Commissioning for New projects |  | Form No: | F7
Board of Director/ Agency approving the Capital cost estimates:
| Date of approval of the Capital cost estimates: | 13.12.2006
|  | Present Day Cost | Completed Cost
| Price level of approved estimates | As of End of 2nd Qtr. Of the year 2014 | As on Scheduled COD of the Station
| Foreign Exchange rate considered for the Capital cost estimates | NA
Capital Cost excluding IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA
| Domestic Component (Rs. Lakhs) | 1648
| Capital cost excluding IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | 1648
IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA
| Domestic Component (Rs. Lakhs) | 94.9
| Total IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | 94.9
| Rate of taxes & duties considered | 12.5% VAT
Capital cost Including IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA
| Domestic Component (Rs. Lakhs) | 1743
| Capital cost Including IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | 1743 | Work in progress
Schedule of Commissioning
COD of Unit-I/ Block-I
COD of Unit-II/ Block-II
-------------------------
---------------------------
| COD of last Unit/ Block | 12 Months
Note:
1. Copy of approval letter should be enclosed.
2. Details of Capital cost are to be furnished as per Form 8 or Form 9 as applicable.
3. Details of IDC & Financing Charges are to be furnished as per Form 10
Petitioner

## T-146 8
Name of Company: |  | #REF! |  | Delhi Transco Ltd
Name of the Project: |  | #REF! |  | Erection, testing, commissioning of 220 KV Double circuit over head tower line to provide infeed to proposed 220KV /66KV Rohini-II S/Strn from existing 400 /220KV S/Stn. Bawana
Name of the Transmission Element: |  | #REF! |  | 220KV Overhead Transmission Line
Break-up of Project Cost for Transmission System |  |  |  |  | Form No: | F8
Rs Crores
No | Break Down | As per original estimates | Actual capital expenditure as on COD | Liabilities/ provisions | Variation (B-C-D) | Reasons for Variation
| A | B | C | D | E | F
A | Transmission Line | l
1 | Preliminary works
1.1 | Design & Engineering
1.2 | Priliminary investigation,Right of way, forest clearance, PTCC , general civil works etc.
| Total Preliminary works | 0
2 | Transmission Lines material
2.1 | Towers Steel | 11280486
2.2 | Conductor | 5568000
2.3 | Earth Wire/OPGW | 962056
2.4 | Insulators | 2669100
2.5 | Hardware Fittings | 609828
2.6 | Conductor & Earthwire accessories | 161260
2.7 | Spares
2.8 | Erection, Stringing & Civil works including foundation | 10740800
| Total Transmission Line Materials | 31991530
3 | Taxes and Duties
3.1 | Custom Duty | 0
3.2 | Other Taxes & Duties | 4722166
| Total Taxes & Duties | 4722166
| Total -Transmission lines | 36713696
B. | Substations
4 | Preliminary works & land
4.1 | Design & Engineering
4.2 | Land
4.3 | Site preparation
| Total Preliminary works & land | 0
5 | Civil Works
5.1 | Control Room & Office Building including HVAC
5.2 | Township & Colony
5.3 | Roads and Drainage
5.4 | Foundation for structures
5.5 | Misc. civil works
| Total Civil Works | 0
6 | Substation Equipments
6.1 | Switchgear (CT,PT, Circuit Breaker, Isolator etc)
6.2 | Transformers
6.3 | Compensating Equipment( Reactor, SVCs etc)
6.4 | Control , Relay & Protection Panel
6.5 | PLCC
6.6 | HVDC package
6.7 | Bus Bars/ conductors/Insulators
6.8 | Outdoor lighting
6.9 | Emergency D.G. Set
6.1 | Grounding System
6.11 | Structure for switchyard
| Total Substation Equipments | 0
7 | Spares
8 | Taxes and Duties
8.1 | Custom Duty
8.2 | Other Taxes & Duties
| Total Taxes & Duties | 0
| Total (Sub-station) | 0
9 | Construction and pre-commissioning expenses
9.1 | Site supervision & site admn.etc.
9.2 | Tools and Plants
9.3 | construction Insurance
| Total Construction and pre commissioning expenses | 0
10 | Overheads
10.1 | Establishment
10.2 | Audit & Accounts
10.3 | Contingency
| Total Overheads | 0
11 | Total Cost (Plant and Equipment) | 36713696
12 | IDC, FC, FERV & Hedging Cost
12.1 | Interest During Construction (IDC) | 9493375
12.2 | Financing Charges (FC)
12.3 | Foreign Exchange Rate Variation (FERV)
12.4 | Hedging Cost
| Total of IDC, FC, FERV & Hedging Cost | 9493375
13 | Capital Cost incl IDC, FC, FERV & Hedging Cost | 46207071 | Work in Progess
Note:
1. In case of time & Cost over run, a detailed note giving reasons of such time and cost over run should be submitted clearly bring out the agency responsible and whether such time & cost over run was beyond the control of the generating company.
Petitioner

## T-146 9
Name of Company: |  | Delhi Transco Ltd
Name of the Project: |  | Erection, testing, commissioning of 220 KV Double circuit over head tower line to provide infeed to proposed 220KV /66KV Rohini-II S/Strn from existing 400 /220KV S/Stn. Bawana
Name of the Transmission Element: |  | 220KV Overhead Transmission Line
Break-up of Construction/ Supply/ Service packages | [6 empty] | Form No: | F9
| Particulars | 1 | 2 | 3 | 4 | 5 | 6 | ----
1 | Name/ No. of Construction / Supply / Service Package
2 | Scope of works1 (in line with head of cost break-ups as applicable)
3 | Whether awarded through ICB/DCB/ Depatmentally/ Deposit Work | DCB
4 | No. of bids received | 3
5 | Date of Award | 09.03.2010
6 | Date of Start of work | 09.03.2010
7 | Date of Completion of Work | Work in progress
8 | Value of Award2 in (Rs. Lakhs) | 359 (ETC portion only)
9 | Firm or With Escalation in prices | with escalation
10 | Actual capitalexpenditure till the completion or up to COD whichever is earlier(Rs.Cr.)
11 | Taxes & Duties and IEDC | Above cost is inclusive
12 | IDC, FC, FERV & Hedging Cost | To be furnished by Finance
13 | Sub -total (9+10+11)
1 The scope of work in any package should be indicated in conformity of Capital cost break-up for the coal/lignite based plants in the Form 8 to the extent possible. In case of Gas/Liquid fuel based projects, break down in the similar manner in the relevent heads as per Form 10.
2 If there is any package, which need to be shown in Indian Rupee and foreign currency(ies), the same should be shown separatly alongwith the currency, the exchange rate and the date e.g. Rs. 80 Cr + US$50 mn = Rs.320 Cr at US$ = Rs 48 as on say 1 April 2011
Petitioner