## f8 SOW & GZP
| Name Of Company | Delhi Transco Limited
| Name of Project | Turnkey Project of Extension of 66 KV bays at 220/66 KV South of Wazirabad & Ghazipur.
Break up of Project Cost for Transmission System |  |  |  |  | Form No: | F 8
No. | Break Down | As per original Estimate (In Crores) | Nov. 2014 (in INR) | Liabilities /Provisions | Variation (B-C-D) | Reason for variation
|  | B | C | D
1 | Preliminary works | NA |  |  | NA
1.1 | Design & Engineering
1.2 | Civil works |  | 0 | 832000
| Total Preliminary works |  | 0 | 832000
2 | Supply of material
2.1 | 220KV Equipments (SF6 CB, CT,CVT,Isolator, LA) |  | 0 | 4,38,98,090
2.2 | 72.5KV Equipments(SF6 CB, CT,CVT,Isolator, LA)
2.3 | NCT,Control and Relay Panel, Terminal Kiosk,
2.4 | Erection, Hardware, ACSR Zebra Conductor, Control cable, Earthing Material
2.5 | Other material
3 | Service Activity
3.1 | ETC of 220KV Equipments (SF6 CB, CT,CVT,Isolator, LA) |  | 0 | 85,32,973
3.2 | ETC of 72.5KV Equipments(SF6 CB, CT,CVT,Isolator, LA)
3.3 | ETC of NCT,Control and Relay Panel, Terminal Kiosk,
3.4 | ETC of Erection, Hardware, Earthing Material
3.5 | Others
4 | Taxes and duties
4.1 | Custom duty
4.2 | Other Taxes and duties (incl. Transportation)
Total Taxes and duties
5 | Other charges
5.1 | Spares parts | NA
5.1 | Type testing & training charges | NA
5.2 | Contingency and Other Charges
5.3 | Engineering & Administrative Charges
6 | Total other charges
6.1 | IDC, FC, FERV & Hedging Cost
6.2 | Capital Cost incl IDC, FC, FERV & Hedging Cost

## f9 SOW & GZP
| Name Of Company | Delhi Transco Limited
| Name of Project | Turnkey Project of Extension of 66 KV bays at 220/66 KV South of Wazirabad & Ghazipur.
Name of the transmission Element
Break-up of Construction/ Supply/ Service packages | [6 empty] | Form No: | F9
| Particulars | 1 | 2 | 3 | 4 | 5 | 6 | ----
1 | Name/ No. of Construction / Supply / Service Package | 1: Extension of 66kV Bays at South of Wazirabad and Ghazipur
| Scope of works1 (in line with head of cost break-ups as applicable) | 1: [a] 1 No. 220KV Bay Equipments and 1 No. 66KV Bay Equipments for 160 MVA 220/66/11KV Power Transformer and associated work at existing 220/66KV station, South of Wazirabad [b] 1 No. 220KV Bay Equipments and 1 No. 66KV Bay Equipments for 160 MVA 220/66/11KV Power Transformer and Additional 1 No. 66 Kv Feeder bay alongwith conversion of existing Twin Zebra 66 kV Busbar to Quad Zebra andassociated work at existing 220/66KV station, Ghazipur
2
3 | Whether awarded through ICB/DCB/ Depatmentally/ Deposit Work
4 | No. of bids received | 1: 02 nos.
5 | Date of Award | 1: 19.06.2014
6 | Date of Start of work | 1: 19.06.2014
7 | Date of Completion of Work | 1: 18.12.2014 (South of Wazirabad) and18.03.2015 (Ghazipur)
8 | Value of Award in (Rs. ) | 1: 5,24,31,063/-
9 | Firm or With Escalation in prices | 1: Firm
10 | Actual capitalexpenditure till the completion or up to COD whichever is earlier(Rs.Cr.)
11 | Taxes & Duties and IEDC | 1: Pertains to Finance deppt.
12 | IDC, FC, FERV & Hedging Cost | 1: Pertains to Finance deppt.
13 | Sub -total (9+10+11) | 1: 5,24,31,063/-(excluding 11&12)
Petitioner

## F14 Mundka (hidden)
Name of Company: |  |  | Delhi Transco Limited
Name of the Project: |  |  | Turnkey Project of Supply, Laying, Jointing, testing and commissioning of 220kV D/C 1x1000 sq.mm U/G XLPE cable from 400/220 kV S/Stn. Mundka to Peeragarhi Sub Stataion. .
Name of the Transmission Element: |  |  | 220 KV D/C Cable
Statement of Additional Capitalisation after COD |  |  |  |  | Form No: | F14
Rs Crores
No | Year | Work/ Equipment proposed to be added after COD up to Cut off Date/ Beyond Cut off Date | Amount capitalised and Proposed to be capitalised | Justification | Regulations under which covered | Admitted Cost1
1
2
3
4
5
Note:
1 Fill the form in chronological order year wise along with detailed justification clearly bring out the necessity and the benefits accruing to the benficiaries.
2 In case initial spares are purchased alongwith any equipment, then the cost of such spares should be indicated separately. e.g. Rotor - 50 Crs. Initial spares- 5 Crs.
Petitioner

## f4 SOW & GZP
Name of Company: |  | Delhi Transco Limited
Name of the Project: |  | Turnkey Project of Extension of 66 KV bays at 220/66 KV South of Wazirabad & Ghazipur.
Name of the Transmission Element:
Abstract of admitted Capital Cost for the existing Project |  |  |  | Form No: | F4
| Particulars | Unit | Details
1 | Capital Cost as admitted by DERC | Rs Lakhs | NA
2 | Capital cost admitted as on |  | 524.31
3 | Foreign Component, if any (In Million US $ or the relevant Currency) | USD | NIL
4 | Domestic Component | Rs Lakhs | 524.31
5 | Foreign Exchange rate considered for the admitted Capital cost |  | NA
6 | Hedging cost, if any, considered for the admitted Capital cost | Rs Lakhs | NA
7 | Total Capital cost admitted (4+5+6) | Rs Lakhs | 524.31
Petitioner

## f7 SOW & GZP
f7
Name of Company: |  | Delhi Transco Limited
Name of the Project: |  | Turnkey Project of Extension of 66 KV bays at 220/66 KV South of Wazirabad & Ghazipur.
Name of the Transmission Element:
Capital Cost Estimates and Schedule of Commissioning for New projects |  | Form No: | F7
| Board of Director/ Agency approving the Capital cost estimates: | DELHI TRANSCO LIMITED
Date of approval of the Capital cost estimates:
|  | Present Day Cost | Completed Cost
| Price level of approved estimates | Nov. 2014 | As on Scheduled COD of the Station
| Foreign Exchange rate considered for the Capital cost estimates | NA | NA
Capital Cost excluding IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA | NA
| Domestic Component (Rs. Lakhs) | 0 | 524.31
| Capital cost excluding IDC, FC, FERC & Hedging Cost (Rs. Lakhs) |  | 524.31
IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA | NA
| Domestic Component (Rs. Lakhs) | Pertain to finance department | Pertain to finance department
| Total IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | Pertain to finance department | Pertain to finance department
Rate of taxes & duties considered
Capital cost Including IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA | NA
| Domestic Component (Rs. Lakhs) |  | 524.31
| Capital cost Including IDC, FC, FERC & Hedging Cost (Rs. Lakhs) |  | Pertain to finance department
Schedule of Commissioning
| COD |  | 18.12.2014 (South of Wazirabad) and 18.03.2015(Ghazipur)
Petitioner