## Index
Name of Company:
Name of the Project:
Name of the Transmission Element:
INDEX OF FORMATS
| Formats |  | PARTICULARS
1 | Form | F1 | Annual Revenue Requirement Summary
2 | Form | F1a | Projection of Sales, Connected Load and Demand
3 | Form | F2 | Details of Transmission Lines and Substations
4 | Form | F2a | Statement of Assets not in Use
5 | Form | F3 | Normative Parameters Considered for Tariff Computations
6 | Form | F4 | Abstract of admitted Capital Cost for the existing Project
7 | Form | F5 | Details of Foreign Loans
8 | Form | F6 | Details of Foreign Equity
9 | Form | F7 | Capital Cost Estimates and Schedule of Commissioning for New projects
10 | Form | F8 | Break-up of Project Cost for Transmission System
11 | Form | F9 | Break-up of Construction/ Supply/ Service packages
12 | Form | F10 | Draw Down Schedule for Calculation of IDC & Financing Charges
13 | Form | F11 | Financial Package Upto CoD
14 | Form | F12 | Details of Project Specific Loans
15 | Form | F13 | Details of Allocation of corporate loans to various transmission projects
16 | Form | F14 | Statement of Additional Capitalisation after COD
17 | Form | F15 | Financing of Additional Capitalisation
18 | Form | F16 | Statement of Capital Cost
19 | Form | F17 | Statement of Capital Works in Progress
20 | Form | F18 | R&M Expenses
21 | Form | F19 | Employee Expenses
22 | Form | F19a | Employee Strength
23 | Form | F20 | Administration & General Expenses
24 | Form | F21 | Fixed Assets and Depreciation
25 | Form | F21a | Consumer contributions and grants towards cost of capital assets
26 | Form | F22 | Interest and Finance Charges
27 | Form | F23 | Statement of Equity
28 | Form | F24 | Return on Capital Employed
29 | Form | F25 | Working Capital Requirements
30 | Form | F26 | Details of Non-tariff Income
31 | Form | F27 | Details of Income from Other Business
32 | Form | F28 | Details of Expenses Capitalised
33 | Form | F29 | Income Tax Provisions
Instructions for the Applicant
1) | Electronic copy in the form of CD/ Floppy Disc shall also be furnished
2) | These formats are indicative in nature and the utility may align the line items to its chart of accounts

## F4 PG
Name of Company: |  | Delhi Transco limited
Name of the Project: |  | 220/33kV GIS at Peeragarhi
Name of the Transmission Element: |  | 220/33kV GIS at Peeragarhi
Abstract of admitted Capital Cost for the existing Project |  |  |  | Form No: | F4
| Particulars | Unit | Details
1 | Capital Cost as admitted by DERC | Rs Crores | 90.37
2 | Capital cost admitted as on |  | Awarded cost 51.23 Crs( including taxes)
3 | Foreign Component, if any (In Million US $ or the relevant Currency) |  | 2881859.81 Euro
4 | Domestic Component | Rs Crores | 31.02
5 | Foreign Exchange rate considered for the admitted Capital cost |  | 60.83
6 | Hedging cost, if any, considered for the admitted Capital cost |  | Nil
7 | Total Capital cost admitted | Rs Crores | 51.23 Crs( including taxes)
Petitioner

## F7 PG
Name of Company: |  | Delhi Transco limited
Name of the Project: |  | 220/33kV GIS at Peeragarhi
Name of the Transmission Element: |  | 220/33kV GIS at Peeragarhi
Capital Cost Estimates and Schedule of Commissioning for New projects |  | Form No: | F7
| Board of Director/ Agency approving the Capital cost estimates: | Board of Directors
| Date of approval of the Capital cost estimates: | 30.09.2011
|  | Present Day Cost | Completed Cost
| Price level of approved estimates | As on November 2014 Qtr. Of the year _________ | As on Scheduled COD of the Station
| Foreign Exchange rate considered for the Capital cost estimates | Pertains to Finance Deptt. | Pertains to Finance Deptt.
Capital Cost excluding IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | 2497041 Euro | 2684859.8 Euro
| Domestic Component (Rs. Lakhs) | 2525.8 + (Custom Duty) | 31.02 Crs.+ 1.46 Crs(PV)
Capital cost excluding IDC, FC, FERC & Hedging Cost (Rs. Lakhs)
IDC, FC, FERC & Hedging Cost
Foreign Component, if any (In Million US $ or the relevant Currency)
| Domestic Component (Rs. Lakhs) | Pertains to Finance Deptt. | Pertains to Finance Deptt.
| Total IDC, FC, FERC & Hedging Cost (Rs. Lakhs) | Pertains to Finance Deptt. | Pertains to Finance Deptt.
| Rate of taxes & duties considered | Pertains to Finance Deptt. | Pertains to Finance Deptt.
Capital cost Including IDC, FC, FERC & Hedging Cost
Foreign Component, if any (In Million US $ or the relevant Currency)
Domestic Component (Rs. Lakhs)
Capital cost Including IDC, FC, FERC & Hedging Cost (Rs. Lakhs)
Schedule of Commissioning
| COD | 27.11.2012 ( scheduled) | 31.01.2015( extended)
Petitioner

## F8 PG
Name of Company: |  | Delhi Transco limited
Name of the Project: |  | 220/33kV GIS at Peeragarhi
Name of the Transmission Element: |  | 220/33kV GIS at Peeragarhi
Break-up of Project Cost for Transmission System |  |  |  |  | Form No: | F8
Rs Crores
No | Break Down | As per original estimates | Actual capital expenditure as on Nov. 2014 | Liabilities/ provisions | Variation (B-C-D) | Reasons for Variation
| A | B | C | D | E | F
B. | Substations
4 | Preliminary works & land
4.1 | Design & Engineering
4.2 | Land | Available | Available
4.3 | Site preparation
Total Preliminary works & land
5 | Civil Works
5.1 | Control Room & Office Building including HVAC | 6.95Cr | 4Cr(Approx) | 1.67Cr | 1.28Cr | Due to Awarded cost
5.2 | Township & Colony
5.3 | Roads and Drainage
5.4 | Foundation for structures
5.5 | Misc. civil works
| Total Civil Works | 6.95Cr | 4Cr(Approx) | 1.67Cr | 1.28Cr
6 | Substation Equipments
6.1 | Switchgear (CT,PT, Circuit Breaker, Isolator etc) | INR56.3596365Cr | Euro2497040.99+ INR181888310.8 | INR38074509.69(to be paid to party) | INR 19.17Cr
6.2 | Transformers
6.3 | Compensating Equipment( Reactor, SVCs etc)
6.4 | Control , Relay & Protection Panel
6.5 | PLCC
6.6 | HVDC package
6.7 | Bus Bars/ conductors/Insulators
6.8 | Outdoor lighting
6.9 | Emergency D.G. Set
6.1 | Grounding System
6.11 | Structure for switchyard
Others
| Total Substation Equipments | INR56.3596365Cr | Euro2497040.99+ INR181888310.8 | INR38074509.69(to be paid to party)
7 | Spares | INR9.0360226 | INR4473725 | Euro144794+INR2413369 | INR 7.2Cr
7.1 | Type test and Training charges |  | 0 | INR4465330.05+Euro43024.80
8 | Taxes and Duties | INR 0.3215021 Cr | INR3.6814482 Cr
8.1 | Custom Duty |  | INR3.6814482 Cr | 220kV GIS spare to be paid after reception | INR 3.3599461
8.2 | Other Taxes & Duties
| Total Taxes & Duties | INR .3215021 Cr | INR3.6814482 Cr |  | INR 3.3599461
Total (Sub-station)
9 | Construction and pre-commissioning expenses
9.1 | ETC charges | INR3.12138 Cr | INR 0.3271255Cr | INR13272560
9.2 | Tools and Plants | NA | NA
9.3 | Transportation & insurance charges | . | INR407448.86 | INR5234303
9.4 | Conigency and other charges | INR3.1227533Cr | NA | NA
| Total Construction and pre commissioning expenses | INR6.2441333 Cr | INR3678704 | INR18506863 | INR40255766
10 | Overheads | NA
10.1 | Establishment
10.2 | Audit & Accounts
10.3 | Contingency
Total Overheads
11 | Total Cost (Plant and Equipment)
12 | IDC, FC, FERV & Hedging Cost
12.1 | Interest During Construction (IDC) | INR5.6338164Cr | Pertains to finance department
12.2 | Financing Charges (FC)
12.3 | Foreign Exchange Rate Variation (FERV)
12.4 | Hedging Cost
12.5 | E & A charges | INR5.8239483Cr
Total of IDC, FC, FERV,E &A charges & Hedging Cost
13 | Capital Cost incl IDC, FC, FERV & Hedging Cost
Petitioner

## F9 PG
Name of Company: |  | Delhi Transco limited
Name of the Project: |  | 220/33kV GIS at Peeragarhi
Name of the Transmission Element: |  | 220/33kV GIS at Peeragarhi
Break-up of Construction/ Supply/ Service packages | [6 empty] | Form No: | F9
| Particulars | 1 | 2 | 3 | 4 | 5 | 6 | ----
1 | Name/ No. of Construction / Supply / Service Package | 1: Establishment of 220/33kV GIS at Peeragarhi
2 | Scope of works1 (in line with head of cost break-ups as applicable) | 1: 220kv Bays -9 Nos , 33kV Bays-14 Nos, 2x100MVA Power Trf.
3 | Whether awarded through ICB/DCB/ Depatmentally/ Deposit Work | 1: ICB
4 | No. of bids received | 1: 8 No
5 | Date of Award | 1: 28.11.2011
6 | Date of Start of work | 1: 28.02.2012
7 | Date of Completion of Work | 1: 27.11.2012(As per schdule)
8 | Value of Award2 in (Rs. Lakhs) | 1: 5123
9 | Firm or With Escalation in prices | 1: Price variation in Trf.
10 | Actual capitalexpenditure till the completion or up to COD whichever is earlier(Rs.Cr.) | 1: 2497041 Euro+INR25.25Cr+INR36814482.49Custom duty)
11 | Taxes & Duties and IEDC | 1: Pertains to Finance department
12 | IDC, FC, FERV & Hedging Cost
13 | Sub -total (9+10+11)
Petitioner