## f8 WZP
| Name Of Company | Delhi Transco Limited
| Name of Project | 220 kV GIS Substation Wazirpur, Delhi.
Name of the transmission Element
Break up of Project Cost for Transmission System |  |  |  |  | Form No: | F 8
No. | Break Down | As per original Estimates | Actual Capital expenditure up to Nov. 2014 | Liabilities /Provisions | Variation (B-C-D) | Reason for variation
| A | B | C | D | E | F
B. | Substations
4 | Preliminary work and land
4.1 | Design & Engineering
4.2 | Land | Available | Available
4.3 | Site Preparation
| Total Preliminary work & Land | 0
5 | Civil Works
5.1 | Control Room & Office Building including HVAC | 63175570 | 39037071.6 | 4337452.4 | 19801046 | The variation in total cost (plant & equipments)is because after estimation the work has been awarded through ICB to the lowest bidder on its quoted price. Balace variation is due to varition during actual execution and furter pending processing of balance payment.
5.2 | Roads and Drainage
5.3 | Foundation of Structures
5.4 | Misc Civil Works
| Total Civil Works | 63175570 | 39037071.6 | 4337452.4 | 19801046
6 | Substation Equipments
6.1 | Switchgear (CT,PT,Circuit Breaker, Isolator and LA etc.) | 404555901 | 296002409.65 | 52235719.35 | 56317772
6.2 | Transformers including accessories
6.3 | Control , Relay and Protection Panel
6.4 | Bus bars/Conductors/insulators
6.5 | Outdoor and indoor lighting
6.6 | Emegency D.G. Set
6.7 | Grounding System
6.8 | Structure for Switchyard
6.9 | Other Equipments
| Total Substation Equipments | 404555901 | 296002409.65 | 52235719.35 | 56317772
7 | Spares
7.1 | Spares parts | 83764618 | 27125900
7.2 | Type testing & training charges |  | 25856782
| Total | 83764618 | 52982682 |  | 30781936
8 | Taxes and duties
8.1 | Custom duty | NA | NA
8.2 | Other Taxes and duties | 2314057 | Included in 6& 7
| Total Taxes and duties | 2314057
| Total (Substation) | 553810146 | 388022163.25 | 56573171.75 | 109214811
9 | Construction and Pre commissining Expenses
9.1 | Erection, Testing and Commissioning Charges | 22466574 | 10035069.3 | 1115007.7 | 11316497
9.2 | Tools and Plants | 0
9.3 | Transportation and Insurance Charges | included in 7 | 14511331
| Total Construction and Pre commissining Expenses | 22466574 | 24546400.3 | 1115007.7 | -3194834
10 | Overheads
10.1 | Establishment | NA
10.2 | Audit & Accounts | NA
10.3 | Contingency | 22418680
| Total Overheads | 22418680
11 | Total Cost (Plant and Equipments) | 573962663 | 412568563.55 | 57688179.45 | 103705920
12 | IDC, FC, FERV & Hedging Cost
12.1 | Interest During Construction (IDC) | 36861329 | Pertains to Finance Department
12.2 | Financing Charges (FC)
12.3 | Foreign Exchange Rate Variation (FERV)
12.4 | Hedging Cost
12.5 | Engineering & Administrative Charges | 36296910
| Total of IDC, FC, FERV & Hedging Cost | 73158239
13 | Capital Cost incl IDC, FC, FERV & Hedging Cost | 671853639

## f9 WZP
| Name Of Company | Delhi Transco Limited
| Name of Project | 220kV GIS S/stn Wazirpur
| Name of the transmission Element | 220/33/11kV S/stn
Break-up of Construction/ Supply/ Service packages | [6 empty] | Form No: | F9
| Particulars | 1 | 2 | 3 | 4 | 5 | 6 | ----
1 | Name/ No. of Construction / Supply / Service Package | 1: Establishment of 220kV GIS at wazirpur, New Delhi
2 | Scope of works1 (in line with head of cost break-ups as applicable) | 1: 7 Nos. 220kV GIS Bay & 2 Nos. 100MVA Power Transformer
3 | Whether awarded through ICB/DCB/ Depatmentally/ Deposit Work | 1: ICB
4 | No. of bids received | 1: 6
5 | Date of Award | 1: 28.05.2010
6 | Date of Start of work | 1: 28.05.2010
7 | Date of Completion of Work | 1: 22.06.2014
8 | Value of Award in (Rs. ) | 1: 48.5 Crore
9 | Firm or With Escalation in prices | 1: Price variation on the cost of Power Transformer & Civil work.
10 | Actual capitalexpenditure till the completion or up to COD whichever is earlier(Rs.Cr.) | 1: 49.0 Crore
11 | Taxes & Duties and IEDC
12 | IDC, FC, FERV & Hedging Cost
13 | Sub -total (9+10+11) | 1: 49.0 Crore
1 The scope of work in any package should be indicated in conformity of Capital cost break-up for the coal/lignite based plants in the Form 8 to the extent possible. In case of Gas/Liquid fuel based projects, break down in the similar manner in the relevent heads as per Form 10.
2 If there is any package, which need to be shown in Indian Rupee and foreign currency(ies), the same should be shown separatly alongwith the currency, the exchange rate and the date e.g. Rs. 80 Cr + US$50 mn = Rs.320 Cr at US$ = Rs 48 as on say 1 April 2011
Petitioner

## F14 Mundka (hidden)
Name of Company: |  |  | Delhi Transco Limited
Name of the Project: |  |  | Turnkey Project of Supply, Laying, Jointing, testing and commissioning of 220kV D/C 1x1000 sq.mm U/G XLPE cable from 400/220 kV S/Stn. Mundka to Peeragarhi Sub Stataion. .
Name of the Transmission Element: |  |  | 220 KV D/C Cable
Statement of Additional Capitalisation after COD |  |  |  |  | Form No: | F14
Rs Crores
No | Year | Work/ Equipment proposed to be added after COD up to Cut off Date/ Beyond Cut off Date | Amount capitalised and Proposed to be capitalised | Justification | Regulations under which covered | Admitted Cost1
1
2
3
4
5
Note:
1 Fill the form in chronological order year wise along with detailed justification clearly bring out the necessity and the benefits accruing to the benficiaries.
2 In case initial spares are purchased alongwith any equipment, then the cost of such spares should be indicated separately. e.g. Rotor - 50 Crs. Initial spares- 5 Crs.
Petitioner

## f4 WZP
Name of Company: |  | Delhi Transco Limited
Name of the Project: |  | 220kV GIS S/stn Wazirpur
Name of the Transmission Element: |  | 220/33/11kV S/stn
Abstract of admitted Capital Cost for the existing Project |  |  |  | Form No: | F4
| Particulars | Unit | Details
1 | Capital Cost as admitted by DERC | Rs Crores | 67.19
2 | Capital cost admitted as on | Rs Crores | 48.5
3 | Foreign Component, if any (In Million US $ or the relevant Currency) | USD | NA
4 | Domestic Component | Rs Crores | 48.5
5 | Foreign Exchange rate considered for the admitted Capital cost |  | NA
6 | Hedging cost, if any, considered for the admitted Capital cost | Rs Crores | NA
7 | Total Capital cost admitted (4+5+6) | Rs Crores | 67.19
Petitioner

## f7WZP
f7
Name of Company: |  | Delhi Transco Limited
Name of the Project: |  | 220kV GIS S/stn Wazirpur
Name of the Transmission Element: |  | 220/33/11kV S/stn
Capital Cost Estimates and Schedule of Commissioning for New projects |  | Form No: | F7
| Board of Director/ Agency approving the Capital cost estimates: | DELHI TRANSCO LIMITED
| Date of approval of the Capital cost estimates: | 16th JUNE 2009
|  | Present Day Cost | Completed Cost
| Price level of approved estimates | As on End of Nov 2014 | As on Scheduled COD of the Station
| Foreign Exchange rate considered for the Capital cost estimates | NA | NA
Capital Cost excluding IDC, FC, FERC & Hedging Cost
| Foreign Component, if any (In Million US $ or the relevant Currency) | NA | NA
| Domestic Component (Rs. Lakhs) | 4740 | 4850.75
Capital cost excluding IDC, FC, FERC & Hedging Cost (Rs. Lakhs)
IDC, FC, FERC & Hedging Cost
Foreign Component, if any (In Million US $ or the relevant Currency)
Domestic Component (Rs. Lakhs)
Total IDC, FC, FERC & Hedging Cost (Rs. Lakhs)
Rate of taxes & duties considered
Capital cost Including IDC, FC, FERC & Hedging Cost
Foreign Component, if any (In Million US $ or the relevant Currency)
Domestic Component (Rs. Lakhs)
Capital cost Including IDC, FC, FERC & Hedging Cost (Rs. Lakhs)
Schedule of Commissioning S/stn commisioned on 22.06.2014
Note:
1. Copy of approval letter should be enclosed.
2. Details of Capital cost are to be furnished as per Form 8 or Form 9 as applicable.
3. Details of IDC & Financing Charges are to be furnished as per Form 10
Petitioner