## Sheet1
NAME OF POWER UTILITY IN DELHI | [8 empty] | DELHI TRANSCO LIMITED
CAPITALIZATION 2015-16
S.No. | Name of Division | Scheme No. | Description of Scheme | Item Name | Item/Unique Code No. | Functional Location | Amount Capitalized | Material Code | Labour & Transportation | Road Restroration Charges | Interest During Construction | Liquidated Damages | A&G Expences | Date of Electrical Inspector Clearence | Date of COD | Remarks
1 | Project - IIA3 | CWO No.AM(F)W/341/09-10 dt 23.04.2009 | 220kV Double Circuit Transmission Line Between 400kV S/Stn. Maharani Bagh and Ghazipur 220kV S/Stn. | Supply, Erection, Testing & Commissioning of 220kV Double Circuit Transmission Line. |  | East Delhi - Yamuna River Bed, Chilla Regulator, Ghazipur Drain, Kondly Bridge | Approx. 1.10 crore |  |  |  | Related to Finance |  |  | Ckt - I; 25/06/2014. Ckt - II; 09/07/2014
2 |  | CWO No ACA(W)/21452/93-94 dated 31.3.94 | 220kV Double Circuit Transmission Line Loop In - loop Out of Bawana - Najafgarh line at Khanjhawala 220kV S/Stn. |  |  | West Delhi - Fafming field of village Karala, Khanjhawala, Madan Pur Dawas. | Approx. 0.08 crore |  |  |  | Related to Finance |  |  | NJF Ckt - I; 29/07/2014. NJF Ckt - II; 29/08/2014 Bawana Ckt - I; 29/07/2014. Bawana Ckt - II; 29/08/2014
3 |  | CWO No.AM(F)W/400/10-11 dt 19.05.2010 | 220kV Double Circuit Transmission Line Loop In - loop Out of Khanjhawala - Najafgarh line at Tikari Kalan (Mundka) 400kV S/Stn. |  |  | West Delhi - Fafming field of village Neelwal, Dichoukalan, Tikari Kalan. | Approx. 10.00 crore |  |  |  | Related to Finance |  |  | Both Circuit commissioned on 16.06.2015
4 |  | CWO No.AM(F)W/369/109-10 dt 24.08.2009 | 220kV Double Circuit Transmission Line Between 400kV S/Stn. Bawana and Rohini - II (Sector - 29) 220kV S/Stn. |  |  | North Delhi - Along with Yamuna Canal in green belt of 45Mtr Road Rohini Sector - 29 | Approx. 08.00 crore |  |  |  | Related to Finance |  |  | Work in Progress
5 | Project-IIBII | CWO No: AM (F) W/371/09-10 dated: 24.08.09 | 220kV D/C U/G 1000 sq.mm. XLPE Cable transmission link between Peeragarhi and Wazirpur | Supply, Erection, Testing & Commissioning of 220kV Double Circuit Transmission Line. |  | Paschim Vihar, Madipur, Punjabi Bagh, Shakurpur, Wazirpur, Wazirpur Industrial area | Approx. 116 Crore |  |  |  | Related to Finance |  |  | Ckt I: 25.12.2015 Ckt II: 04.02.2016 |  | USD 1 = INR 67
6 | Project-IIBII | SAP No: CT220-14/001 | 220kV S/C U/G 1000 sq.mm. XLPE Cable transmission link between Gazipur to Patparganj |  |  | Gazipur to Patparganj | Approx. 9.92 crore |  |  |  | Related to Finance |  |  | Both Circuit commissioned on 31.03.2015
7 | Project-IIBII | SAP No: CT220-13/006 | 220kV D/C U/G 1000 sq.mm. XLPE Cable transmission link between Vasant Kunj and R.K.Puram and Wazirpur |  |  | Vasant Kunj to R.K.Puram | Approx. 70.19 crore |  |  |  | Related to Finance |  |  | Both Circuit commissioned on 24.11.2015 |  | USD 1 = INR 67
8 | Project IIAI | CWO No: AM (F) W/371/09-10 dated: 24.08.09 | 220kV D/C U/G 1000 sq.mm. XLPE Cable transmission link between Mundka and Peeragarhi |  |  | Tikri Kalan, Ghevra Mod, Mundka, Nangloi, Udyog Nagar, Peeragarhi, Paschim Vihar | Approx. 105 crore | [6 empty] | Ckt 1: 31.3.2015 Ckt II: 29.4.2015
CAPITALIZATION 2016-17
9 | Project-IIAII | SAP No: CT220-13/006 | 220kV D/C U/G 1200 sq.mm. XLPE Cable transmission link between Harsh Vihar, Preet Vihar and Patparganj | Supply, Erection, Testing & Commissioning of 220kV Double Circuit Transmission Line. |  | Harsh Vihar to Preet Vihar to Patparganj | Approx. 250 Crore |  |  |  | Related to Finance |  |  | Work under progress and likely to be completed by May 2016 |  | Approx. 125 Crore payment processed till date
10 | Project-IIAI | SAP No: CT220-15/008 | 220kV S/C U/G XLPE Cable transmission link between Park Street, electric Lane and IP |  |  | Park Street, Electric Lane and IP | Approx. 126 Crore |  |  |  | Related to Finance |  |  | Work under progress |  | Approx. 33.2 Crore payment processed till date